## Sheet1
ID	Work Summary	Description	Estd. Time(hours/days)	Status(Complete/Not started/In Progress)
	Registration/Verification page form refinement		0.5	0.5
	SSO module spruce up
	Mail Body refinement	Verification mail to be enhanced with proper look and feel.	0.5	0.5
		Welcome mail need to be added tied to a cron job.	0.5	0.5
		cc mail of registration mail to admin account.

	New Home page Site design	New Layout changes.	1	1
		Widget implementation to display sample SVG.	0.5
		New Sign-up and Sign in forms.
		Captcha support	0.5	0.5

	Page Loading optimization
	Adding Resending Mail if not received		0.5

	Start Working on SRS of Gallery app
	.htacces documents		0.5
	Feedback interface	Mail it to Rajarshi@webionix.com and store it to DB.	1 day	1

		total		4

	Integrate the Wordpress blog		2 days
	Robot.txt integration for		0.5 day
	Index.php for URL display
	Sitemap.xml
	Adding video interface on the spot help		1.5 day